## SCHEDULE
Project | Dept. | 2017 | 2018 | 2019 | 2020 | 2021 |  | Project | Dept. | 2022 | 2023 | 2024 | 2025 | 2026
Air Compressor | Fire |  | 61700
Ladder Truck | Fire |  |  |  |  | 425000
Rescue Vehicle | Fire |  | 244754
Self Contained Breathing Appara | Fire |  |  |  |  | 170000
Second Floor Remodeling | Fire |  |  |  | 120000
HVAC System I | Fire | 9600
HVAC System II | Fire |  | 9600
Masonary Restoration | Library |  | ?
Carpet 2nd floor | Police |  |  | 6000
Basement Reconstruction | Police |  | 9000
Handicap Ramp Repair | Police | 3000
Rear Parking lot reconstruction | Town H |  | 12000
New Small Dump Truck | Highway |  | 90000 |  |  |  |  | Street Light Replacement |  |  |  |  | 50000
New Large Dump Truck | Highway |  | 160000
New Highway Facility | Highway |  | ?
Deerfield Rd. Paving Phase II | Highway |  | 89600
Deerfield Rd. Paving Phase I | Highway | 99200
Martinson Ln. Paving | Highway | 42240
Highfield Dr. Paving | Highway | 31200
Albin Ave. Paving | Highway |  | 42720
Pine Acres Rd. Paving | Highway |  | 50560
Whitten St. Catchbasins | Highway |  |  | 7600
Whitten St. Sidewalks | Highway |  |  | 29750
Whitten St. Paving | Highway |  |  | 26667
Webster St. Catchbasins | Highway |  |  | 8300
Webster St. Sidewalks | Highway |  |  | 29750
Webster St. Paving | Highway |  |  | 26667
Mt. Delight Rd. Paving | Highway |  |  |  | 118880
Gilbert Rd. Paving | Highway |  |  |  | 63840
Project | Dept. | 2017 | 2018 | 2019 | 2020 | 2021
Summers Ave. Paving | Highway | [5 empty] | 30880
Valley St. Paving | Highway | [5 empty] | 27520
Valley St. Sidewalk | Highway | [5 empty] | 25387
Reserve St. Paving | Highway |  |  |  |  | 17920
Reserve St. Sidewalk | Highway |  |  |  |  | 18550
Theodore Ave. Paving | Highway |  |  |  |  | 18112
Theodore Ave. Sidewalk | Highway |  |  |  |  | 18060
Willow St. Paving | Highway |  |  |  |  | 17920
Elm St. Paving | Highway | [5 empty] | 11200
Elm St. Sidewalk | Highway | [5 empty] | 11375
Birchwood Dr. Paving | Highway |  |  |  |  | 94800
TOTAL COST PROJECTION |  | 187257 | 771952 | 136753 | 304740 | 782383 | 106362
TOTAL CIP Cost Projection |  | 2289447

## FUNDING
Funding Source | Dept. | 2017 | 2018 | 2019 | 2020 | 2021 | Shortfall | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
Budget-Fire Engine Lease | Fire | N/A |  |  |  | 84000 |  | 2022: 84000; 2023: 84000; 2024: 84000; 2025: 84000
Budget-Fire Rescue Veh. | Fire |  | 84000 | 84000 | 84000
Budget-Fire Compressor | Fire |  | 12300 | 11063 | 11063 | 11063 |  | 2022: 11063
CRF-Fire Safety Equip. | Fire | 124228 |  |  |  |  | 45772
CRF-Fire Equip | Fire | 575
CRF-PS Facilities | Fire/Police | 16260 |  |  |  |  | 220940
CRF-Town Hall Maint. | TH | 19321
CRF-Library | Library | 10221 |  |  |  |  | 16609
Budget-Dump Trk. Lease | HWY | N/A | N/A | 33692 | 33692 | 33692 |  | 2022: 33692; 2023: 33692
Budget-Sml. Dump Trk Le | HWY | N/A | N/A | 30500 | 30500 | 30500
Budget-Road Construction | HWY | 183737 | 183737 | 183737 | 183737 | 183737
CRF-HWY Equip. | HWY | 12000
CRF-HWY Garage | HWY | 201883
Sale of Land-Hynes |  | 302600
Sale of Land-2 Parcels |  | 76600
Total Shorfall |  | 947425 | 280037 | 342992 | 342992 | 342992 | 283321 | 2022: 128755; 2023: 117692; 2024: 84000; 2025: 84000